## Beerus
PROJECT TITLE
Beerus |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead Robbie Mckennie
Project Start Date: | 2024-02-22 |  |  |  |  | February | [13 empty] | March | [27 empty] | April
Scrolling Increment: | 0 | time axis 2024-02-22 to 2024-04-17
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-02-22 to 2024-04-17
Iteration !
Complete Iteration One | Goal | Corbyn, Joel, Robbie | 100% | 2024-02-22 | 21 | 2024-02-22: 2; 2024-02-23: 2; 2024-02-24: 2; 2024-02-25: 2; 2024-02-26: 2; 2024-02-27: 2; 2024-02-28: 2; 2024-02-29: 2; 2024-03-01: 2; 2024-03-02: 2; 2024-03-03: 2; 2024-03-04: 2; 2024-03-05: 2; 2024-03-06: 2; 2024-03-07: 2; 2024-03-08: 2; 2024-03-09: 2; 2024-03-10: 2; 2024-03-11: 2; 2024-03-12: 2; 2024-03-13: 2
Planning Meeting Report | Low Risk | Corbyn | 100% | 2024-02-22 | 7
Complete Stakeholder Registry | High Risk | Joel | 100% | 2024-02-29 | 7
Design/Test Three Personas | Low Risk | Robbie, Joel | 100% | 2024-03-07 | 6
Complete/Review Progress Report | Milestone | Corbyn, Joel, Robbie | 100% | 2024-03-13 | 1 | bar: 2024-03-13
Iteration 2
Complete Iteration 2 | Goal | Corbyn, Joel, Robbie | 100% | 2024-03-14 | 21 | 2024-03-14: 2; 2024-03-15: 2; 2024-03-16: 2; 2024-03-17: 2; 2024-03-18: 2; 2024-03-19: 2; 2024-03-20: 2; 2024-03-21: 2; 2024-03-22: 2; 2024-03-23: 2; 2024-03-24: 2; 2024-03-25: 2; 2024-03-26: 2; 2024-03-27: 2; 2024-03-28: 2; 2024-03-29: 2; 2024-03-30: 2; 2024-03-31: 2; 2024-04-01: 2; 2024-04-02: 2; 2024-04-03: 2
Planning Meeting Report | Low Risk | Robbie, Joel | 100% | 2024-03-14 | 5
Complete Resource Needs | Med Risk | Corbyn, Joel, Robbie | 100% | 2024-03-19 | 4
Create Gantt Chart | Low Risk | Corbyn | 100% | 2024-03-23 | 7
Implement GitHub Features | Med Risk | Joel, Robbie | 100% | 2024-03-30 | 4
Complete/Review Progress Report | Milestone | Corbyn,Joel, Robbie | 100% | 2024-04-03 | 1 | bar: 2024-04-03
Iteration 3
Complete Iteration 3 | Goal | Corbyn, Joel, Robbie | 75% | 2024-04-03 | 27 | 2024-04-03: 2; 2024-04-04: 2; 2024-04-05: 2; 2024-04-06: 2; 2024-04-07: 2; 2024-04-08: 2; 2024-04-09: 2; 2024-04-10: 2; 2024-04-11: 2; 2024-04-12: 2; 2024-04-13: 2; 2024-04-14: 2; 2024-04-15: 2; 2024-04-16: 2; 2024-04-17: 2
Planning Meeting Report | Low Risk | Corbyn | 100% | 2024-04-03 | 4
Complete Risk Register | High Risk | Joel | 100% | 2024-04-07 | 7
Website Itergration/Publishing | High Risk | Corbyn, Robbie | 90% | 2024-04-14 | 10
User Testing | Med Risk | Corbyn, Robbie | 0% | 2024-04-24 | 5
Complete/Review Progress Report | Milestone | Corbyn, Joel, Robbie | 0% | 2024-04-29 | 1